## Buyer
Sr No | Module | Delivery | Efforts
1 | Sign in / Sign up / Forgot password / Social media registration and sign in |  | 60 | Phase 1
2 | Choose location from available list or search based on address |  | 24 | Phase 2
3 | Dashboard |  | 84 | Phase 3
4 | Mark as favorite / My favorites list |  | 18 | Phase 4
5 | Messages |  | 64 | Phase 5
5.1 | Inbox / sent items |  |  | Phase 6
5.2 | Compose message with HTML editor option
5.3 | Deleted / mark as read / unread
5.4 | Email notifications on registered email with each new message
6 | My Orders |  | 24
6.1 | Place new order |  | 24
6.2 | Manage my cart |  | 18
6.3 | Confirm order with order details + delivery option |  | 12
6.4 | Payment processing |  | 62
7 | Order tracking (will be done once the mobile app is in place)
8 | My Wallet |  | 22
Add money in wallet (directly through payment gateway)
Withdraw money ( by sending a request to admin)
9 | Edit profile / Personal info |  | 8
10 | Reviews |  | 14
10.1 | Provide reviews
10.2 | My Reviews
11 | Search using filters on website |  | 38
| Total |  | 472

## Merchant
Sr No | Module | Linked to | Efforts
1 | Sign in / Sign up / Forgot password / Social media registration and sign in |  | 4
2 | Dashboard |  |  | Phase 1
3 | Messages |  | 12 | Phase 2
3.1 | Inbox / sent items |  |  | Phase 3
3.2 | Compose message with HTML editor option |  |  | Phase 4
3.3 | Deleted / mark as read / unread |  |  | Phase 5
3.4 | Email notifications on registered email with each new message |  |  | Phase 6
4 | My Orders |  | 26
4.1 | List of orders received by restaurant
4.2 | Manage orders with status to update them
5 | Order tracking (will be done once the mobile app is in place)
6 | My Wallet
6.1 | Withdraw money ( by sending a request to admin) |  | 8
7 | Edit profile / Personal info |  | 12
8 | Reviews |  | 12
9 | Manage restaurant users |  | 18
9.1 | add / edit / delete
10 | Manage food category |  | 10
11 | Manage food items per category |  | 26
12 | Manage restaurant |  | 24
12.1 | Images
12.2 | Basic info
12.3 | Timings
12.4 | Tax info
12.5 | Delivery option
12.6 | Description
13 | Manage about us |  | 8
14 | Google map display based on restaurant address |  | 8
15 | My Settings |  | 12
15.1 | Deleivery / Change password / Deactivate account / Delete permanent
16 | My Coupons |  | 24
16.1 | Add coupons / Edit
| Total |  | 204

## Super admin
Sr No | Module | Linked to | Efforts
1 | Manage city list for buyer and merchant |  | 16
2 | Manage User messages for buyers and merchant |  | 18 | Phase 1
3 | Manage orders for buyer and merchant |  | 16 | Phase 2
4 | Manage wallet for buyer and merchant |  | 22 | Phase 3
5 | Manage buyers on website (Add / edit / delete / de-activate) |  | 26 | Phase 4
6 | Manage restaurants (Add / edit / delete / de-activate) |  | 6 | Phase 5
7 | Manage restaurant users |  | 12 | Phase 6
8 | Manage restaurant food category |  | 8
9 | Manage food items for restaurants |  | 12
10 | Manage restaurant information including basic / tax / etc |  | 12
11 | Approve / manage reviews |  | 8
12 | View / Manage restaurant settings |  | 6
13 | Manage restaurant coupons |  | 18
14 | Manage Bringly fee / percentage per transaction / order / one time |  | 24
| Total |  | 204

## Hidden
Sr No | Module | Linked to | Efforts
1 | Social media integration |  | 16
2 | Search city based on address (location integration) |  |  | Phase 1
3 | Payment gateway integration |  | 90 | Phase 2
4 | Email on place order / receive order |  | 28 | Phase 3
5 | Signal R for messages / Unread sms concept |  | 8 | Phase 4
6 | Maintain activity log with login |  | 16 | Phase 5
7 | Maintain error log |  | 12 | Phase 6
8 | Deploy test environment |  | 16
9 | Deploy live environment |  | 16
| Total |  | 202

## Summary
Phase | Total Hours | Expected roll out
Phase 1 | 94 | 2017-12-18
Phase 2 | 136 | 2018-01-08
Phase 3 | 286 | 2018-02-05
Phase 4 | 170 | 2018-03-01
Phase 5 | 226 | 2018-03-28
Phase 6 | 170 | 2018-04-18
1082

## Sprints
Sprint | Phase | Phase Point | Efforts | Total Hours | Estimated date
1 | 1 |  |  | 50 | 2018-01-29
Buyer_2
Buyer_4
Buyer_9
2 |  |  |  | 44 | 2018-02-12
Merchant_2
Merchant_7
Super Admin_1
Hidden_8
3 | 2 | Buyer_5 |  | 96 | 2018-03-16
Buyer_5.1
Buyer_5.2
Buyer_5.3
Buyer_5.4
Buyer_6.2
Buyer_10
Buyer_10.1
Buyer_10.2
4 |  | Merchant_3 |  | 40 | 2018-03-27
Merchant_3.1
Merchant_3.2
Merchant_3.3
Merchant_3.4
Merchant_8
Hidden_1
Hidden_2
5 | 3 | Buyer_3 |  | 286 | 2018-06-01
Buyer_1
Buyer_6
Buyer_6.3
Merchant_1
Merchant_4
Merhcant_4.1
Merhcant_4.2
Merchant_13
Merchant_14
Merchant_15
Merchant_15.1
Merchant_16
Merchant_16.1
6 | 4 | Buyer_6.4 |  | 92 | 2018-07-07
Buyer_8
Merchant_6
Merchant_6.1
|  | Merchant_9 |  | 78 | 2018-08-01
Merchant_9.1
Merchant_10
Merchant_11
Merchant_12
7 |  | Merchant_12.1
Merchant_12.2
Merchant_12.3
Merchant_12.4
Merchant_12.5
Merchant_12.6
8 | 5 | Buyer_11 |  | 126 | 2018-09-03
Super_Admin_2
Super_Admin_3
Super_Admin_4
Super_Admin_5
Super_Admin_6
9 |  | Super Admin_7 |  | 100 | 2018-09-30
Super_Admin_8
Super_Admin_9
Super_Admin_10
Super_Admin_11
Super_Admin_12
Super_Admin_13
Super_Admin_14
10 | 6 | Hidden_3 |  | 170 | 2018-10-28
Hidden_4
Hidden_5
Hidden_6
Hidden_7
Hidden_9
| Total |  |  | 1082